OdishaInfra Mobile Application — Scope of Work Real Estate Discovery Platform for Odisha · iOS & Android Prepared by Qwegle Technologies Pvt. Ltd. · April 2026 · Confidential

Client; OdishaInfra (Client / Product Owner). Service Provider; Qwegle Technologies Pvt. Ltd., Bhubaneswar. Document Type; Scope of Work (SoW) — Enterprise Mobile Application. Platform; iOS (14+) & Android (10+) — React Native / Flutter. Version; v1.0 — April 2026. Classification; Confidential.

# 1. Executive Summary

OdishaInfra is a mobile-first real estate discovery platform exclusively focused on the Odisha property market. The platform connects verified homebuyers directly with RERA-registered developers and builders, eliminating broker friction while ensuring rigorous lead quality through the OdishaInfra validation team acting as a trusted intermediary.

This Scope of Work document outlines the complete engagement between Qwegle Technologies Pvt. Ltd. (Service Provider) and OdishaInfra (Client) for the design, development, testing, and deployment of the OdishaInfra mobile application across iOS and Android platforms. The engagement is structured across three phases spanning twelve months from project kickoff.

## 1.1 Key Objectives

- Deliver a production-ready iOS and Android application serving three user types: Customers, Developers/Builders, and OdishaInfra Admins

- Implement a 20-second property listing workflow for developers with AI-assisted descriptions

- Build an AI-powered natural language property search engine using the Anthropic Claude API

- Create a TikTok-style Shorts/Reels feed for property video discovery

- Establish a rigorous callback and lead validation CRM for the OdishaInfra team

- Integrate Firebase Analytics and Facebook SDK for performance marketing infrastructure

- Deliver a secure, offline-capable, WCAG 2.1 AA compliant application

## 1.2 Platform at a Glance

| Dimension | Detail |
| --- | --- |
| Platform | iOS 14+ and Android 10+ (React Native or Flutter) |
| User Types | Customer · Developer/Builder · OdishaInfra Admin |
| Total Screens | 24 screens across 3 portals (S01–S10, D01–D07, A01–A07) |
| Key Differentiator | All leads validated by OdishaInfra before reaching developer |
| AI Feature | Claude API (claude-sonnet-4-20250514) for natural language search |
| Analytics | Firebase Analytics + Facebook SDK (Meta Pixel) |
| Localisation | English v1 · Odia language in Phase 3 |
| Auth | OTP via SMS · Google OAuth (customer optional) |

# 2. Project Scope

## 2.1 In-Scope Features

Customer Application (S01–S10)

- Splash/Onboarding screen with animated logo reveal and Customer vs. Developer CTA split

- Home Feed with featured listings, nearby properties, filter chips, and pull-to-refresh

- Search screen with real-time text search, location chip filters, and AI search widget

- Property Detail screen: image carousel, spec grid, Google Maps embed, developer card, callback CTA

- Shorts/Reels Feed: TikTok-style full-screen vertical scroll with autoplay, wishlist, share, and callback

- Wishlist: saved properties with price-change indicators and quick callback access

- Account screen: stats, callback history, notifications settings, edit profile, logout

- Callback Modal: OdishaInfra-branded bottom sheet, phone pre-fill, time preference, toast confirmation

- OTP Login: phone entry, 6-digit OTP, 30-second resend, 3-attempt lockout, profile setup

- Notification Centre: categorised alerts, FCM deep links, empty state

Developer Portal (D01–D07)

- Developer Dashboard: KPI cards (projects, interests, callbacks, short views), 7-day analytics snapshot

- My Projects: list with active/inactive toggle, status badges, interest counts, archive/delete

- Quick Add Property: 4-step wizard completing in ~15 seconds — Basic Info, Photos, Location Pin, Publish

- Edit Project: full form covering all 25+ schema fields, media upload, amenities, documents

- Upload Shorts: video picker (max 60s/50MB), link to project, caption, thumbnail, HLS transcoding

- Leads Overview: anonymised callback queue — status Pending / Validated / Connected

- Developer Analytics: views, saves, shorts views, callbacks over time with CSV export

Admin Panel (A01–A07)

- Admin Dashboard: platform-wide KPIs, system health indicators (API/AI/CDN), real-time activity feed

- Lead Validation CRM: callback review queue with overdue alerts, call/validate/reject workflow, customer data reveal post-validation

- Developer KYC Review: RERA verification, document approval/rejection, activation workflow, 24–72hr SLA

- Listings Moderation: featured listings management, new property review queue, moderation actions

- User Management: customer and developer lists, search, block/unblock, registration analytics

- Push Notifications: FCM broadcast composer with audience targeting by city, campaign history with open rates

- Platform Analytics: conversion funnel, city traffic breakdown, session metrics, retention data

## 2.2 Out-of-Scope (v1)

- Broker registration and commission tracking portal (planned for Phase 3 / v2)

- Odia language localisation (Phase 3 — Months 7–12)

- 360-degree virtual tours (Phase 3)

- Customer document upload for pre-qualification (Phase 3)

- Property comparison and EMI calculator (Phase 2 — Months 4–6)

- Web application or admin web dashboard (mobile-only v1)

- Payment gateway or booking deposit collection

- Third-party CRM integration (e.g., Salesforce, Zoho) — OdishaInfra uses in-app CRM only in v1

# 3. Technical Architecture

## 3.1 Recommended Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | React Native (or Flutter) | Single codebase for iOS & Android; large talent pool; hot reload for faster iteration |
| Backend API | Node.js (Express) or Go | High concurrency for real-time feeds; REST + WebSocket for notifications |
| Database | PostgreSQL (primary) | Relational schema for users, properties, callbacks; JSONB for flexible property fields |
| Media Storage | AWS S3 + CloudFront CDN | Scalable image/video storage; CloudFront for low-latency media delivery across Odisha |
| Video Transcoding | AWS MediaConvert / FFmpeg | HLS transcoding for adaptive streaming of Shorts/Reels |
| Auth | Firebase Auth / Custom OTP | OTP via SMS gateway (Msg91 / Twilio India); JWT refresh tokens |
| AI Search | Anthropic Claude API | claude-sonnet-4-20250514; serverless function wrapper; rate limiting middleware |
| Push Notifications | Firebase Cloud Messaging | FCM for iOS + Android; topic-based targeting by city |
| Analytics | Firebase Analytics + Facebook SDK | Dual-track: product analytics + performance marketing attribution |
| Maps | Google Maps SDK | Property location pin, nearby landmarks, native Maps deep link |
| Hosting | AWS / GCP (India region) | Mumbai region for low latency; auto-scaling for traffic spikes |

## 3.2 Security Architecture

- JWT auth tokens with refresh mechanism stored in iOS Keychain / Android Keystore

- HTTPS only for all API calls (TLS 1.2+); no plaintext communication

- Phone numbers hashed (SHA-256) in transit; raw customer contact data never transmitted to developer endpoints

- Role-based access control: Customer / Developer / Admin with separate API route guards

- Admin Panel accessible only from whitelisted IP ranges with 2FA enforcement

- DPDP Act (India) compliance: data minimisation, consent flows, user data deletion support

- App Tracking Transparency (iOS 14.5+) permission flow before Facebook SDK data collection

## 3.3 Performance Targets

| Metric | Target |
| --- | --- |
| Cold start launch time | < 2 seconds |
| Screen transition time | < 300 ms |
| API response time (p95) | < 500 ms |
| AI Search response time | < 3 seconds end to end |
| App download size — iOS | < 30 MB |
| App download size — Android | < 25 MB |
| Image load (progressive) | Blur placeholder → full within 1 second on 4G |
| Video autoplay start | < 1.5 seconds on 4G |

# 4. Project Phases & Deliverables

## Phase 1 — MVP  (Months 1–3)

Delivers the core customer and developer experience. This phase is the foundation for market entry, onboarding the first 50 developers and opening the platform to early customer users.

| Module | Deliverable | Screen(s) |
| --- | --- | --- |
| Onboarding & Auth | Customer OTP login, Developer OTP + KYC registration, Splash screen | S01, S09 |
| Home Feed | Featured listings, nearby section, filter chips, skeleton loading, pull-to-refresh | S02 |
| Property Detail | Image carousel, spec grid, Google Maps, callback CTA, wishlist toggle | S04 |
| Text Search | Real-time debounced search, location chip filters | S03 |
| Wishlist | Save/unsave, price-change indicator, quick callback | S06 |
| Callback Flow | OdishaInfra-branded callback modal, backend lead creation, status tracking | S08 |
| Shorts Feed | Full-screen vertical scroll, autoplay, location filter, wishlist, share | S05 |
| Account | Profile, stats, callback history, notification settings, logout | S07 |
| Notifications | FCM setup, notification centre, deep links | S10 |
| Developer Portal | Full portal — Dashboard, My Projects, Quick Add, Edit, Shorts Upload, Leads, Analytics | D01–D07 |
| Admin Panel | Full admin panel — Dashboard, Lead CRM, KYC Review, Moderation, Users, Push, Analytics | A01–A07 |
| Analytics Setup | Firebase Analytics + Facebook SDK initialisation, core event tagging | All |
| Backend API v1 | All REST endpoints, PostgreSQL schema, S3 media setup, CDN configuration | – |
| DevOps | CI/CD pipeline, staging + production environments, iOS TestFlight + Android Play Beta | – |

## Phase 2 — Growth  (Months 4–6)

Adds the AI-powered search, push campaigns, richer developer analytics, and utility features that drive retention and conversion.

| Feature | Description |
| --- | --- |
| AI Search (Claude API) | Natural language query integration with claude-sonnet-4-20250514, rate limiting (10/hr/user), streaming response, fallback handling, vector pre-filter for >200 properties |
| Push Notification Campaigns | Admin-initiated FCM campaigns by city/segment, open-rate tracking, scheduled sends |
| Developer Analytics v2 | Detailed funnel breakdown, short completion rates, export to CSV, comparative period analysis |
| Property Comparison | Side-by-side comparison of up to 3 properties from search/wishlist |
| EMI Calculator | In-app calculator: loan amount, interest rate, tenure with amortisation table |
| AI Property Description | Developer can generate property description from uploaded photos using Claude API (D03 Quick Add) |
| Performance Optimisation | Lazy loading improvements, image compression pipeline, cache strategy tuning |

## Phase 3 — Scale  (Months 7–12)

Expands language accessibility, adds immersive features, and introduces the Broker Portal — opening a new channel for lead generation at scale.

| Feature | Description |
| --- | --- |
| Odia Language | Full UI localisation to Odia language for tier-2 city penetration (Sambalpur, Berhampur, Balasore) |
| Virtual Tours | 360-degree property tour embedding via third-party SDK (Matterport / custom WebGL viewer) |
| Document Upload | Customer income proof / KYC upload for pre-qualification before callback — reduces junk leads |
| Verified Listings Badge | OdishaInfra site-visited and verified badge, manual admin trigger post physical site inspection |
| Broker Portal v2 | Controlled broker registration, commission tracking, sub-lead assignment, payout reporting |
| Advanced CRM | Lead scoring, follow-up reminders, bulk status update, CRM export for developer's internal use |

# 5. Team Composition

Qwegle Technologies will deploy a dedicated cross-functional team for the duration of the engagement.

| Role | Responsibility | Phase |
| --- | --- | --- |
| Project Manager | Client communication, sprint planning, risk tracking, milestone sign-off | All Phases |
| UI/UX Designer | Design system, all 24 screens (Figma), prototyping, user testing coordination | Ph 1–2 |
| Mobile Lead (React Native / Flutter) | Architecture, state management, performance, App Store submissions | All Phases |
| Mobile Developer | Feature implementation across Customer, Developer, and Admin screens | All Phases |
| Backend Developer | REST API, database schema, auth, media pipeline, webhook integrations | All Phases |
| DevOps / Cloud Engineer | CI/CD, AWS infra, CDN setup, monitoring, alerting | Ph 1 setup + ongoing |
| QA Engineer | Test plans, regression suite, device matrix testing, App Store review preparation | Ph 1–3 |
| AI Integration Specialist | Claude API integration, prompt engineering, rate limiting, vector search setup | Ph 2 |

# 6. Project Timeline

| Week | Milestone | Phase |
| --- | --- | --- |
| Week 1–2 | Project kickoff · Requirements sign-off · Design system setup · Repository and CI/CD initialisation | Phase 1 |
| Week 3–4 | Figma designs complete for all 24 screens · Client design review and approval · Backend schema v1 | Phase 1 |
| Week 5–8 | Customer app core screens (S01–S10) development · Developer portal (D01–D07) development | Phase 1 |
| Week 9–10 | Admin panel (A01–A07) development · Firebase + Facebook SDK integration · Internal QA round 1 | Phase 1 |
| Week 11–12 | Bug fixes · Performance testing · TestFlight + Play Beta release · Client UAT (User Acceptance Testing) | Phase 1 |
| Month 3 End | Phase 1 Sign-off · App Store + Google Play submission · MVP Live | Phase 1 Close |
| Month 4–5 | AI Search integration · Push notification campaigns · Developer Analytics v2 · EMI Calculator | Phase 2 |
| Month 6 | Property comparison · Phase 2 QA · Play Store + App Store update · Phase 2 sign-off | Phase 2 Close |
| Month 7–10 | Odia localisation · Virtual tours · Document upload · Verified badge system | Phase 3 |
| Month 11–12 | Broker portal v2 · Advanced CRM · Final QA · Phase 3 delivery and handover | Phase 3 Close |

# 7. Investment & Pricing

The following investment structure covers design, development, testing, deployment, and 30-day post-launch hypercare support for each phase.

| Phase | Scope Summary | Duration | Investment (INR) |
| --- | --- | --- | --- |
| Phase 1 — MVP | 24 screens · 3 portals · Backend API · DevOps · QA · App Store submission | 3 months | ₹ 8,50,000 |
| Phase 2 — Growth | AI Search · Push campaigns · Comparison · EMI calculator · Analytics v2 | 3 months | ₹ 3,50,000 |
| Phase 3 — Scale | Odia language · Virtual tours · Document KYC · Broker portal · Advanced CRM | 6 months | ₹ 5,00,000 |
| Total Engagement | Full 12-month product development and delivery | 12 months | ₹ 17,00,000 |

## 7.1 Payment Milestones — Phase 1

| Milestone | Amount (INR) | Trigger |
| --- | --- | --- |
| Project Kickoff | ₹ 2,12,500 | 25% — Contract signature and project initiation |
| Design Approval | ₹ 1,70,000 | 20% — Client approval of all Figma screens |
| Development Complete | ₹ 2,55,000 | 30% — Internal QA passed, staging environment live |
| UAT Sign-off | ₹ 1,27,500 | 15% — Client user acceptance testing complete |
| App Store Live | ₹ 85,000 | 10% — Both iOS and Android apps live on respective stores |

## 7.2 Additional Cost Items

- Cloud infrastructure (AWS/GCP): estimated ₹ 15,000–25,000/month depending on traffic (billed separately)

- Anthropic Claude API: billed per token — estimated ₹ 8,000–15,000/month at 5,000 AI searches/day

- SMS OTP gateway (Msg91): approximately ₹ 0.15 per OTP; estimate ₹ 5,000–10,000/month

- Google Maps Platform: pay-per-use; estimated ₹ 5,000–8,000/month at moderate scale

- Firebase (Blaze plan): estimated ₹ 3,000–5,000/month for FCM, Analytics, and Auth at scale

- Annual Maintenance Contract (post Phase 3): ₹ 1,50,000/year — bug fixes, OS updates, minor feature work

Note: All prices are exclusive of applicable GST (18%). A formal commercial proposal with GST invoice will be issued upon SoW sign-off.

# 8. Deliverables Checklist

| # | Deliverable | Format | Phase |
| --- | --- | --- | --- |
| 1 | Clickable UI/UX prototype (Figma) | Figma share link | Ph 1 |
| 2 | Design system and component library | Figma + exported tokens | Ph 1 |
| 3 | Source code — mobile app (React Native / Flutter) | Private Git repository | Ph 1–3 |
| 4 | Source code — backend API | Private Git repository | Ph 1–3 |
| 5 | API documentation | Swagger / Postman collection | Ph 1 |
| 6 | Database schema and migration scripts | SQL files | Ph 1 |
| 7 | Admin Panel — web-accessible or in-app | React Native / Web | Ph 1 |
| 8 | TestFlight and Google Play Beta build | App builds | Ph 1 |
| 9 | iOS App Store listing (live) | App Store Connect | Ph 1 |
| 10 | Google Play Store listing (live) | Play Console | Ph 1 |
| 11 | Firebase Analytics dashboard setup | Firebase console access | Ph 1 |
| 12 | Facebook SDK and pixel configuration | Meta Events Manager | Ph 1 |
| 13 | AI Search integration (Claude API) | Backend service + app integration | Ph 2 |
| 14 | Odia language localisation strings | i18n JSON files | Ph 3 |
| 15 | Broker portal module | In-app portal | Ph 3 |
| 16 | QA test reports (each phase) | PDF reports | Ph 1–3 |
| 17 | Deployment and maintenance runbook | Markdown / PDF | Ph 3 |
| 18 | 30-day post-launch hypercare (each phase) | Dedicated support channel | Ph 1–3 |

# 9. Assumptions & Exclusions

## 9.1 Assumptions

- Client will provide all brand assets, logo files, content, and sample property data within 5 business days of project kickoff

- Client will designate a single point of contact (SPOC) with authority to approve designs and sign off on milestones

- Client holds valid App Store Connect (Apple Developer) and Google Play Console accounts or will provide access credentials

- Client will obtain and provide Anthropic API key, Google Maps API key, and Firebase project credentials

- UI/UX mockup revisions are limited to 2 rounds per phase; additional revision rounds billed at ₹ 15,000 per round

- Third-party SMS gateway account (e.g., Msg91) to be set up and funded by the client

- Backend hosting accounts (AWS / GCP) to be under client ownership; Qwegle to configure and deploy

- Legal review of Privacy Policy and Terms of Service is client's responsibility

## 9.2 Exclusions

- App Store Optimization (ASO) copywriting beyond initial listing setup

- Paid digital advertising campaigns (covered in the separate Marketing Strategy document)

- Physical site visits for property verification (OdishaInfra's operational responsibility)

- Call centre or telephony infrastructure for lead validation team

- Custom ERP or third-party CRM integration (scoped separately if required)

- Data migration from any existing system

- Hardware or device procurement for testing

# 10. Change Management

Any scope additions, deletions, or modifications to this SoW will be handled through a formal Change Request (CR) process. Changes will not be implemented until written approval is obtained from the client.

| Step | Action | Owner |
| --- | --- | --- |
| 1 | Change request raised by client or Qwegle via email | Requesting party |
| 2 | Impact assessment: scope, timeline, cost | Qwegle PM |
| 3 | CR document issued with revised estimates | Qwegle PM |
| 4 | Client review and written approval (email or DocuSign) | Client SPOC |
| 5 | CR incorporated into sprint plan and billing | Qwegle PM |

Minor changes (no timeline or cost impact) will be logged and acknowledged within 1 business day. Major changes will receive a full CR document within 3 business days of request.

# 11. Terms & Conditions

## 11.1 Intellectual Property

Upon receipt of final payment for each phase, all IP developed under this SoW — including source code, designs, and documentation — transfers fully to the client (OdishaInfra). Third-party libraries and APIs remain subject to their respective licences.

## 11.2 Confidentiality

Both parties agree to maintain strict confidentiality of all proprietary information shared during the engagement. This includes product roadmaps, user data, API credentials, and commercial terms. NDA execution recommended prior to project kickoff.

## 11.3 Warranty & Support

- 30-day hypercare period following each phase go-live: critical bug fixes at no additional cost

- Post-warranty support available under Annual Maintenance Contract (AMC) at ₹ 1,50,000/year

- Response SLA during hypercare: Critical (P1) — 4 hours · Major (P2) — 1 business day · Minor (P3) — 3 business days

## 11.4 Governing Law

This Scope of Work is governed by the laws of India and the state of Odisha. Any disputes shall be subject to the exclusive jurisdiction of courts in Bhubaneswar, Odisha.

| For OdishaInfra Authorised Signatory Name: ___________________________ Date: ____________________________ | For Qwegle Technologies Pvt. Ltd. Founder & CEO Nick · Qwegle Technologies Date: ____________________________ |
| --- | --- |

OdishaInfra Mobile App — Scope of Work v1.0  ·  Qwegle Technologies Pvt. Ltd.  ·  Bhubaneswar, Odisha  ·  April 2026